## Accounts
34 Rolwy Dr. Palgrave
Statement of project cost
August 10-2024
| Payment | Expenses | Construction Management | Expense category | Remaining Budget | Project Name: | Text Input | Ceate a project name
TOTAL | 30000 | 28089.59 | 4213.4385 |  | -2303.0285 | Location | Text Input
|  | 2027.69 |  | Plywood |  | Date | Select from drop down calender
|  | 3900.01 |  | Studs - 2x4 and 2x6 for Walls |  | Report: | Project cost | Text input
|  | 4386.3 |  | Joists and Rim Board and 2x6x 12' new wall
|  | 1437.7 |  | 3/4" ply |  | Payment, Expenses, CMF | Columns that are $ values
|  | 1200 |  | Bin |  | Remaining Budget | Formaula: Total - sum of Expenses and Construction Management
|  | 225.6 |  | Tarp
|  | 8000 |  | Demolition |  | Payment | Amount - Entered by user
|  | 2912.29 |  | Trusses |  | Expenses | Amount - Entered by user
|  |  |  | Windows |  | Expense Category | Selected from a data base of items that user can search by type and then select
|  | 4000 |  | Framing Deposit

## changes
34 Rowly Dr, Palgrave
Item | Activity | Item Description | Impact
1 | Demolition and disposal | Only the staircase | Full Ceiling subfloor on Garage
2 | Framing
2.1 | 2 x 6 wall in Garage | Not in original scope | New work due to site condition. Supply and Install
2.2 | TJI 560 at 12" c/c for full Garage ceiling | Only in area of stair case removal | Supply and Install Joists
2.3 | Sub floor over the Garage | Only in area of stair case removal | Supply and Install plywood subfloor and insulation

## Scope of work
34 Rowly Drive
| Demolition | 2000
| Electrical | 20000
| Plumbing | 30000
| HVAC | 20000
Plumbing Accessories
| Trusses | 5000
Ceiling joists
| Framing | 7500
| Drywall | 7500 | 1280 | 0.6 | 4 | 0.5 | 6528
| StairCase | 6600
| Paint | 5000 | Full house
103600
Stucco
Shingles
Sheathing
Insulation
Flooring - Hardwood
Flooring - Porcelain
Doors
Windows
Caulking
Baseboard

## Sheet3
|  |  | Materials |  | Labour
|  |  | Unit Price | Total | Unit Price | Total
Basement
Drywall |  | 2400 | 0.6 | 1440 | 4 | 9600 | 11040
Framing | [6 empty] | 0
Insulation |  | 2400 | 0.6 | 1440 | 1 | 2400 | 3840
Fire code for basement
Paint |  | 4000 | 0.5 | 2000 | 0.5 | 2000 | 4000
Electrical |  | 29550 |  |  |  |  | 29550
Plumbing |  | 28000 |  |  |  |  | 28000
HVAC |  | 10000 |  |  |  |  | 10000
Trusses
Lumber
Framing 2nd Floor
Windows
Doors
Stucco
Flooring
Basement
Main Floor
2nd Floor new
Replace carpet with hardwood
Stair case | [6 empty] | 6000
Crane | [6 empty] | 1000
Basement
Floor | 1140 | 6 | 6840 | 2 | 2280 |  | 9120
Bathroom 1 | 42 | 6 | 252 | 8 | 336 |  | 588
Bathroom 1 | 20 | 6 | 120 | 8 | 160 |  | 280
Mainfloor |  |  | 0 |  | 0 |  | 0
Flooring - wood | 1215 |  | 0 |  | 0 |  | 0
Bathroom | 30 | 6 | 180 | 8 | 240 |  | 420
2nd Floor |  |  | 0 |  | 0 |  | 0
Wood floor | 1370 | 6 | 8220 | 6 | 8220 |  | 16440
| 81 | 6 | 486 | 8 | 648 |  | 1134
| 64 | 6 | 384 | 8 | 512 |  | 896
| 180 | 6 | 1080 | 8 | 1440 |  | 2520
Framing
Length of wall | 110 | 8 | 880 | 9 |  |  | 7920
Installation of trusses | [6 empty] | 9000
Bin | [6 empty] | 2000
Container | [6 empty] | 600
Portable Toilet | [6 empty] | 200
Plumbing Accessories
WC
Bidet
Sink
Pace Price for Trusses | [6 empty] | 3120
147668